## Build guide
DIY Mini-Airboat — step-by-step build guide (riveted aluminum hull) (rev 7)
DIY hours assume a skilled backyard mechanic with a pneumatic rivet gun, who can TIG-weld aluminum and has a small shop. Pro cost is labor only (materials are in the BOM workbook), at roughly $90-100/hr shop rates.
Step | DIY time (hours) | Pro cost, labor only ($) | Key checks
Hull (riveted aluminum)
1. Export flat patterns of every skin panel, frame and stringer from the CAD in OnShape; print full-size templates | 6 | 450 | Check bottom blank 60 x 150 in incl. rocker
2. Build a level strongback with station molds at each frame position | 10 | 700 | Twist-free to 1/16 in end to end
3. Order 5052-H32 sheet; have a fab shop shear the blanks and brake the 45 deg chine bends and transom flanges | 4 | 600 | Pro cost here = shear and brake service
4. Cut and form stringers (hat or angle sections) to the rocker curve; cut ribs and frames from angle; notch a 1 x 3/4 in limber in every bay of every frame and a cross-drain slot in every stringer at x 3.5-4.5 | 19 | 1480 | Stringers line up under the UHMW strip edges; deburr and prime every notch
5. Cleco frames and stringers together on the jig; check square and diagonals; rivet the framing | 14 | 1100
6. Fit the bottom sheets: flat to x = 120 in, then the conic roll-up tangent into the 15 deg raked bow plate; centerline seam over a doubled center stringer; cleco and trim | 12 | 950 | Sides angle in to the 45 in bow plate; only one long bottom seam
7. Fit chine/side panels, bow face and transom; cleco every lap (1 in minimum); check symmetry and chine angle | 12 | 900
8. Drill all rivet holes to final size (3/16 in, double rows at about 3/4 in spacing); deburr both sides | 12 | 900 | About 2,000 holes
9. Take laps apart, clean, prime faying surfaces, butter with sealant (Sikaflex 291 or 3M 4200), rivet with closed-end aluminum blind rivets | 22 | 1700 | Wet sealant squeeze-out along every seam
10. Install engine beds (doubled aluminum stringers + plates on HDPE), cage mount plates, aluminum rub rail at the sheer | 8 | 600 | Bed plates level side to side within 1/16 in
11. Leak test: hull on stands, fill with 4 in of water, check the outside (before UHMW) for 24 h; mark and fix leakers. Repeat with UHMW on, watching the strip edges | 8 | 600 | Drill out and replace any weeping rivet; Gluvit on weeping laps
12. Fit UHMW strips; through-bolt into the stringers with sealant, slotted toward the ends; fit the nose cap | 12 | 900 | Fix strips at mid-length only
13. Self-etching primer and topcoat | 10 | 900
Drivetrain
14. Find a G13 (Metro 1.3 or Swift), compression-test it; replace timing belt, water pump, gaskets, plugs | 16 | 1100 | Compression even across cylinders
15. Measure the bellhousing pattern; machine the adapter plate and jackshaft housing; fit the flex coupling | 12 | 1000 | Jackshaft runout under 0.003 in
16. Build engine mounts with polyurethane bushings; set the engine low on the bed plates | 8 | 650 | Crank 15 in above the hull bottom
17. Fabricate and TIG-weld A-frames, gusset peak plates, feet, diagonal braces, tie struts | 30 | 2500 | Peak plates parallel and the shaft bores in line
18. Build the tension yoke; machine the prop shaft and flange; mount the flange bearings | 14 | 1150
19. Install pulleys, belt and optional idler; align pulleys with a straightedge or laser; set tension with the jack screw | 6 | 450 | Tighten slot bolts first, pivot bolts last
20. Mount the prop; set pitch with the protractor; track the blades | 4 | 350 | Blade tips track within 1/8 in
21. Mount the radiator on the cradle; plumb hoses; fill and bleed coolant | 6 | 450
22. Build the exhaust: raised muffler on hangers from the starboard engine-bed plate, above the aft foam, with a heat shield; flex section after the manifold; tailpipe over the transom | 14 | 1150 | Muffler clear of the foam and the belt; tailpipe below the prop disk
23. Fuel system and throttle cable | 6 | 450
Prop cage, rudders and steering
24. Have the two 72.4 in hoops rolled; cut and fit legs, rails, EMT; weld the cage | 20 | 1700 | Grind zinc off EMT before welding; ventilate
25. Fit 1/2 in hardware cloth front, aft and sides; install the shaft sleeve; paint | 10 | 750 | At least 4.7 in from mesh to any blade
26. Make the honeycomb rudders: cut, edge channels, seal edges, hinge tubes | 12 | 950 | No open cells anywhere
27. Steering: horns, tie bar, pushrod, rod ends, lever pivot; set rudders parallel | 10 | 800 | Full lock both ways without touching the cage
Floor, seating, controls and flotation
28. Open sump: install pump, float switch with cycle counter, outside-reachable auto/off/manual switch, bailer, 1 in drain plug, through-hull and raised FRP grate box; pour a bucket in each bay and check it reaches the sump | 7 | 560 | Bailer check valve works; every bay drains; pump switch reachable from the water
29. Make the 24 foam blocks (20 thin blocks aft of x = 72 in, 4 bow blocks): pour urethane foam per bay onto release-lined Coroplast trays (or into molds), trim to fit with 1/16 in clearance, seal-coat, glue on HDPE pads | 12 | 950 | Urethane only; nothing bonded to the hull; blocks lift out
30. Make bolt-down floor panels resting on the stringer tops, and the bow shelf (sealed 3/8 in plywood or 0.063 in aluminum), on rivnuts and gasket tape; cut and fit 8 deck plates | 12 | 950 | Panels hold the blocks down if swamped; floor drains aft to the sump
31. Build the bench: 1/2 in ply box with a sealed bottom panel and bulkhead at x = 87 in; battery bay forward with an Al ledge ring, EPDM gasket and a flush lid bolted into clip nuts; dry storage / cooler aft with a flush padded lid hinged on the starboard top corner, locking stays at both ends, rubber T-latch and a 1 in drain plug | 22 | 1700 | Hose-test both lids; the cooler lid stops at 95 deg and rests open
32. Backrests, grab handles (loop 10.5 in off centre), engine guard, footrest ladder, rung-mounted throttle pedal (arm, torsion spring, rest stop), padded cushions | 14 | 1100 | Pedal clears the next rung fully pressed on every rung
33. Mold or cut the strap-in foam side blocks (taller with the low floor); fit straps | 6 | 450 | They provide the swamped stability: always strapped in
Joint details, rev 6 (added work only; base fabrication is in the sections above)
34. Cut plates from the DXF flat patterns (plasma or waterjet, or send out); deburr, drill to final size | 4 | 300 | Check hole positions against the fab workbook
35. Cut tubes per the cut list: mitre leg ends, slot leg tops 3/8 x 2.5, cope cage tubes (hole saw or notcher) | 4 | 300 | Dry-fit every joint before welding
36. Weld the A-frame weldments in a jig: legs into peak plate, caps, crossbar, feet, gussets, clevis tabs | 3 | 250 | Peak plates parallel, shaft bores in line; weld alternately to limit distortion
37. Build the engine-mount cradles and engine-side brackets; fit poly bushings and through-bolts | 4 | 350 | Drill brackets to the real block's mount bosses
38. Fit braces with clevis bolts, tie struts, radiator mounts and stays, exhaust hangers and saddle | 3 | 250 | Everything removable unbolts without cutting
39. Cage: weld coped nodes, drill and bolt the steel pads over HDPE isolators; fit rudder pivots, rod ends, tie bar | 3 | 250 | Rudders swing freely lock to lock
40. Bench sockets, handle flanges, clips, battery tray, steering pivot, ladder feet, bow-shelf angles and padeyes | 4 | 300 | Backrests drop in and pin; shelf solid underfoot
Electrical, finish and testing
41. Battery bay power: Group 31 AGM; 4 AWG fusible link and 1/0 red to the sealed main switch on the bench front (rubber gasket, studs inside the bay); 60 A MRBF and 6 AWG red to the 12-way hub, 6 AWG black return; 10 A MRBF at battery + for the bilge; 4 relays on the port wall, 2 dimmers on the starboard wall (see the wiring schematic) | 10 | 800 | Every circuit fused at its source: 10 A max on 18 AWG, 20 A only on 12 AWG
42. Build and fit the adjustable trim tab | 4 | 300
43. Ground runs: tach sweep, belt tension and flap, cooling, vibration; re-torque all bolts | 8 | 650 | Listen for rough rpm bands
44. Dock tests: float level, bilge pump, optional swamp test | 4 | 300
45. Water trials: trim tab and prop pitch setup, steering, planing two-up | 8 | 650
46. Registration, numbering, safety gear check | 2 | 150
Rev 7 additions: driver station, lights, searchlight, power, deck hardware, safety, electrical
47. Driver side frame: cut and TIG-weld the two 2 x 2 posts, top rail, cross arms, 2 x 3 inner rail, knee braces, diagonal and hull-side clips; bolt the base plates through the floor and the clips through backing plates (aft pair also through frame x96) | 14 | 1100 | Leg space 11 in from the bench side to the braces; frame rock-solid under a hard pull
48. Armrest pad and grip: bend the 1 in 316 stick, weld it into the inner rail, fit the ball knob; set the armrest height (drv_armrest_h) and reach (drv_reach) to the driver | 4 | 300 | Hand lands on the knob seated against the backrest, forearm on the pad
49. Dash: cut the 7 in panel, weld the stalk, fit the tach, water temp and fuel gauges, key switch, trouble light, lanyard kill switch, 12 V socket and USB with flaps; mount the phone holder | 6 | 450 | Panel faces the eye; flaps seal
50. Light switch panel (two OFF-LO-MED-HI rotaries, nav rocker) and inclinometers: mount on the cross arms; zero the bubbles with the boat level on calm water | 2 | 150 | Both bubbles readable from the seat
51. Cage light bar and searchlight: clamp the brackets over the front hoop, fit the turret and yoke, mount the remote control on the aft cross arm, run the two push-pull cables along the hull side, cage leg and front hoop; adjust so the handle and grip track the light | 8 | 650 | Full yaw and pitch with no binding; cables clear of the prop
52. Throttle cable: run from the pedal anchor through glands in the bench walls and bulkhead, through the engine-guard grommet to the throttle body; leave a 6 in service loop in the bench | 3 | 250 | Full throttle at full pedal; snaps back to idle
53. Deck hardware: weld the bow knees, bolt the four cleats (bow on the knees, stern on the transom corners), weld the bow-eye strap and fit the ring | 4 | 300 | Cleats through-bolted with backing
54. Safety gear: B-1 extinguisher bracket (starboard) and air-horn bracket (port) on the bow shelf | 1 | 75 | Extinguisher charged; reachable
55. Engine harness: 1-1/2 in PVC conduit along the cooler bottom port corner (sealed through the bulkhead and aft wall); 1/0 red to the starter B+ and 1/0 black to the block ground stud, booted; 5/8 in engine loom (EFI, start, pump, tach, temp, trouble, bilge) to the DT12 + DTP2 engine connector; 3-hole guard grommet; bilge and float-switch branches with DT2s; fuel pump and filter on the port bed plate | 10 | 800 | Cables clamped every 12 in, clear of the belt, brace and exhaust; start relay clicks on START
56. Dash and lights harness: two PG13 glands in the bay starboard wall; dash loom and lights-power loom along the deck cable cover and up the aft post; dash loom along the arm and inner rail to the dash and switch panel; lights loom to the light bar, searchlight and stern light; DT/DTP connectors at every device | 10 | 800 | Each rotary steps the light through LO-MED-HI; kill lanyard stops the engine
57. Nav lights and fuel sender: bow combination light on its stanchion at the bow shelf front, all-round white on the 18 in mast on the aft hoop, bow loom under the starboard gunwale flange; electric sender in the tank with a DT2 at the tank front | 4 | 300 | Sidelights and all-round light visible from every bearing; fuel gauge reads full and empty
58. Sound check: measure dBA at 50 ft at idle, cruise and full throttle before using noise-limited waters | 2 | 150 | Record the numbers for lake officials
Total
DIY weekends at 16 hours each
Blue numbers are estimates you can edit; section rows and totals recalculate.
Comparison: stitch-and-glue hull version
Hull section only | 204 | 15850
Whole boat | 480 | 37850
Saved with the riveted aluminum hull (whole boat)
Values above come from the stitch-and-glue build guide (DIY-Mini-Airboat_Build-Guide.xlsx).